## Sheet1
Risk ID | Description of Risk | Likelihood | Consequence | Risk Rating | Action Plan
R1 | Data breach in sensitive customer information | Likely | Critical | High | Implement advanced cybersecurity measures
R2 | Project funding falls through unexpectedly | Occasional | Moderate | High | Prepare contingency funding options
R3 | Modified contractual requirements lead to delays | Seldom | Marginal | Medium | Include buffer time for potential contract changes
R4 | Natural disaster disrupts project timeline | Unlikely | Catastrophic | Extreme | Develop an emergency response plan
R5 | Key personnel illness or resignation affects project | Occasional | Moderate | High | Cross-train staff to handle absences